## Sheet1
Data Center Relocation / Migration Checklist
Project Planning
| FALSE | For large moves, choose an experienced, certified moving company with data center experience.
| FALSE | Establish and practice coordination between the data center movers and in-house staff
|  | FALSE | Develop a budget and Data Center Relocation Blueprint, including:
|  | FALSE | Planning time and effort
|  | FALSE | New facility acquisition, evaluation, and renovation cost
|  | FALSE | Additional staff
|  | FALSE | Overtime
|  | FALSE | Relocation company cost
|  | FALSE | Risk identification
|  | FALSE | Contingency plan
|  | FALSE | Possible server replacement or diversification
|  | FALSE | Cooling requirements
|  | FALSE | Infrastructure acquisitions and modifications
|  | FALSE | Wiring/cabling
| FALSE | Schedule all deployment and re-installation events
| FALSE | Verify inventory of all hardware and virtual system elements noting:
|  | FALSE | Equipment condition
|  | FALSE | Size
|  | FALSE | Weight
|  | FALSE | Serial numbers
| FALSE | Review and update the full system diagram
Pre-Deployment Documentation, Warranty, and Insurance Coverage
| FALSE | Review equipment manufacturer warranties
|  | FALSE | Current coverage
|  | FALSE | Possible limitations affecting installation or removal of servers
| FALSE | Verify and review internal insurance policies
| FALSE | Verify and understand mover’s insurance coverage terms and conditions
Pre-Server Deployment
| FALSE | Prepare the target server area
|  | FALSE | Network connectivity
|  |  | FALSE | Ensure Internet connectivity
|  |  | FALSE | Layout/server room diagram
|  |  | FALSE | Network cabling
|  |  | FALSE | Power management
|  |  | FALSE | Rack placement
|  |  | FALSE | VPNs
|  |  | FALSE | DNS
| FALSE | Prepare in-house deployment participants
|  | FALSE | Safety procedure training
| FALSE | Training session/rehearsal of the server deployment protocol, including:
|  | FALSE | Labeling and packing equipment
|  | FALSE | Cables
|  | FALSE | Rails
| FALSE | Pair experienced partners with first-timers
| FALSE | Remind staff of availability and importance of the data center lift for server:
|  | FALSE | Installation/removals
|  | FALSE | Transportation
|  | FALSE | Positioning
| FALSE | Arm leaders with program timelines and server room diagram
| FALSE | Advise staff and clients of upcoming system downtime
| FALSE | Schedule project manager to work onsite from start through sign-off
Preparing In-House Hardware and Software
| FALSE | Review and update diagrams and lists for each rack
|  | FALSE | Verify in-cabinet physical availability
|  | FALSE | Verify safe stored backup copy
| FALSE | Verify 100% backup of virtual assets
| FALSE | Identify and schedule upgrades to perform during migration
| FALSE | Inventory all hardware and virtual system elements
| FALSE | Identify and remove unnecessary abandoned cables
| FALSE | Charge and inspect server lift
| FALSE | Verify truck availability
| FALSE | Verify availability of impact, moisture, and other hazards resistant packing materials
Execution of Server Deployment
| FALSE | Mirror power requirements when changing cabinets
| FALSE | Shut down servers, storage, and networking devices according to established protocol
| FALSE | Inspect, clean, repair, and re-inventory all items prior to reloading racks
| FALSE | Project manager sign-off on hardware list and scheduled tests once all items deployed and inventoried